## Slide 1: M_o_R® Management of Risk Practitioner
        2010 edition - English
This material contains diagrams and text information based upon:
Management of Risk® manual 2010
PRINCE2®, PRINCE2 Agile® , ITIL® , M_o_R® , MoP® , MoV®, MSP® , P3O® , P3M3®, P2MM® are registered trade marks of AXELOS Limited, used under permission of AXELOS Limited.
All rights reserved.
The Swirl logo™ is a trade mark of AXELOS Limited, used under permission of AXELOS Ltd.
Version 1.0
Notes: Shown at the start of day 1 – as candidates come into the room (confirming they are at the right address)

## Slide 2: M_o_R® Practitioner - Day 1

## Slide 3: Welcome
Teambuilding and focus
  Name
  Background
  Current role
  Experience in Risk Management
  Motivation to participate in this course
Notes: Practitioner courses are usually small groups of specialists and experience project / programme managers who want to develop further. Their interest is in the subject matter and less in passing the exam.
This material attempts to achieve both by letting them apply the guidance to their own experience.
It is therefore important to take time here to research their motivation to participate and prepare them for the application of M_o_R to their own situation

## Slide 4: Purpose of the course
To provide delegates with a thorough understanding of the Management of Risk: Guidance for Practitioners
After completing this training course participants will be able to apply all parts of the Guidance to real life situations
Delegates are enthused and eager to apply the theory to practice
To prepare delegates for the M_o_R Practitioner exam
Notes: By combining the theory with the daily practice of the delegates the application of the Guidance is practiced and the complexity and use of the framework is made apparent.
By spreading the three days out over a three week period, the delegates will have ample time to make practice exams, study and reflect.
(The main objective is to understand M_o_R and to be able to apply M_o_R in order to improve and speed up decision making.
To prepare delegates for M_o_R Practitioner exam is an important
side-effect)

## Slide 5: Practitioner Planning
Course outline
3 day training course + exam on day 4
(often spread out over a period of about 3 weeks)
Homework after every training day
(in all 20 to 26 hours of homework)
Prerequisite for Practitioner exam:
Must have passed the M_o_R Foundation exam
Notes: Make the delegates aware of their own responsibility during the training course to study and do their homework.

## Slide 6: “Tabbing”
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Notes: Focus on the Guidance!
This is all there is. Getting to know what the guidance is about and where information is at can be assisted using tabs. Link this to the open book practitioner exam and explain some details of it.
Relate the book to the Syllabus that is present in their student manual and explain how the syllabus can be used as a checklist for their studying to pass the exam.

## Slide 7: Recap of the Foundation level
Notes: Participants will take the M_o_R foundation sample paper 1.
Let them check their answer and explain which Syllabus area still needs improving.

## Slide 8: The Best Practice Guides
P3M3®, M_o_R®, MoV®,P3O®, ITIL®, Resilia®, ITIL Maturity Model®, MSP®, PRINCE2® and PRINCE2 Agile® are registered trade marks of AXELOS Limited, used under permission of AXELOS Limited.

## Slide 9: What is ‘Risk’?
M_o_R defines risk as…..
An uncertain event or set of events that, should it occur, will have an effect on the achievement of objectives.
A risk is measured by the combination of the probability of a perceived threat or opportunity occurring and the magnitude of its impact on objectives (page 4)
Ref. 1.2
Notes: Introduce the Glossary in the back of the book and explain it’s use.
Show how the Syllabus prescribes the knowledge of the glossary as speaking one language and using uniform terminology is part of the objective of the training course and using the guidance in practice.
Relate the definition to the fact that thus risk management will likely improve performance against objectives – whatever they may be.

## Slide 10: What is ‘Risk Management’?
M_o_R defines Risk Management as…..
“The systematic application of principles, an approach and a process to the tasks of identifying and assessing risks, and then planning and implementing risk responses”(page 4)
The aim is to support proactive decision-making through a good understanding of risks and their likely impact.
Ref. 1.3
Notes: Introduce the Glossary in the back of the student manual and explain it’s use.
Show how the Syllabus prescribes the knowledge of the glossary as speaking one language and using uniform terminology is part of the objective of the training course and using the guidance in practice.

## Slide 11: Risk Management
Risks need to be:
Identified – consider uncertainties and describe them for a common understanding
Assessed – Estimate probability, impact and proximity, prioritize and understand the overall level of risk
Controlled – planning appropriate responses and implement and monitor these
Note the importance of communication within and between all these areas.
Ref. 1.3
Notes: The orange words make the link between what you’re doing as an organisation and the process model

## Slide 12: The Benefits of Risk Management
Provides more informed decision-making capability
Improves the decision-making process
Improves ability to respond to change
Helping the organisation to fulfil policies or legal requirements
Improves the organisation’s quality of services
Increases revenue and/or reduces costs, while maintaining quality
Ref. 1.4
Notes: See also the benefits of Risk Management in chapter 1 (1.4)
Relate to the definition of RM to the improved performance against objectives – this shows what kind of objectives there may be.

## Slide 13: The Benefits of Risk Management
Fewer sudden shocks and unwelcome surprises
More efficient use of resources
Reduced waste and fraud, and better value for money
Better service delivery
Reduction in management time spent fire-fighting
Better management of contingent and maintenance activities
Lower cost of capital
Improved innovation
Increased likelihood of change initiatives being achieved
More focus internally on doing the right things properly
More focus externally to shape effective strategies
Ref. 1.4
Notes: Relate to the definition of RM to the improved performance against objectives – this shows what kind of objectives there may be.

## Slide 14: Threat or Opportunity?
Threat - an uncertain event that could have a negative impact on objectives or benefits
Opportunity - an uncertain event that could have a favourable impact on objectives or benefits
Ref. 1.2
Notes: Threat or Opportunity?
Objective: Hosting a BBQ people will still remember for years to come.
Bad weather, Weather forecast: It will be cloudy and rain is expected.
Threat or Opportunity? Or Both in this Case?

## Slide 15: Risk Cause, Event, and Effect
Risk Cause
  Describes the source of the risk - the event or situation that gives rise to the risk - often referred to as risk drivers
  Not risks in themselves, but the potential trigger points for risk
  May be either internal or external to the organisational activity under consideration
Risk Event - describes the area of uncertainty in terms of the threat or the opportunity
Risk Effect - describes the impact that the risk would have on the organisational activity should the risk materialise
Notes: Risk Cause, Event, and Effect
Objective: Hosting a BBQ people will still remember for years to come.
Weather forecast: It will be cloudy and rain is expected.
Risk Cause: Bad weather
Risk Event: it might rain during the BBQ
Risk Effect: People will not enjoy the BBQ in the rain

## Slide 16: Probability, Impact, EV & Proximity
Probability
  probability selected from the scales in the risk management strategy
  where appropriate pre and post response action probabilities should be recorded
Impact
  impact selected from the scales in the risk management strategy
  where appropriate pre and post-response action impacts should be recorded
Expected Value
  EV = average impact X probability percentage
Proximity
  the date when the risk is anticipated to materialize

## Slide 17: Risk response and status
Risk response category - selected from the options in the risk management strategy (e.g. threat reduction, opportunity enhancement)
Risk tolerance – the threshold levels of risk exposure which, when exceeded, trigger an escalation
Risk response - actual action to be taken recorded together with any trigger dates
Risk status (active or closed)
Notes: Risk Category
Risk category can be derived from the risk breakdown structure or a risk prompt list. If no risks have been recorded against a particular category this is an immediate indication to re-examine (early warning indicator)
Example of risk categories:
(At strategic level but also usable at project level)
Strategic/commercial
Economic/financial/market
Legal/contractual/regulatory
Organizational/management/human factors
Equality/discrimination
Political/societal factors
Environmental factors/acts of God (force majeure)
Technical/operational/infrastructure

## Slide 18: Risks and risk exposure
Inherent risk – the exposure arising from a specific risk before action has been taken to manage it
Residual risk – what risk still remains (after the response is applied)
Secondary risk –a new risk that has been introduced by a risk response
Risk exposure – the extent of risk borne by the organization at that time
Notes: For secondary risk – refer to the risk register A.4 where more explanation is given

## Slide 19: Recent Developments
2002 M_o_R in response to Turnbull
2002 Sarbanes-Oxley (SOX)
2004 Basel II accord
2004 Code Tabaksblat (NL)
2006 Combined codes for Corporate Governance (UK)
2007-2008 Worldwide financial crisis
2009 ISO 31000 Risk Management Principles and Guidelines
2010 Refresh of M_o_R and Basel III accords
2018 ISO 31000:2018 refresh
Ref. 1.5

## Slide 20: Corporate Governance
“is the system by which organisations are directed and controlled.”
The Boards of directors are responsible for governance in their organisation
The Shareholders appoint directors and auditors to ensure governance is in place
The board sets the strategic aims, provides leadership, supervises management and reports to shareholders
The Audit Committee supports the Board and the Accounting Officer by reviewing the comprehensiveness and reliability of assurance
Ref. 1.6
Notes: Remember Nick Leeson, infamous investment officer who speculated and brought bankruptcy on a global bank in 1995 (Barings Bank now part of ING). This was a cause for more corporate governance
You need to have control and grip on financial/operational compliance and your threats and opportunities (risks)
By using M_o_R you are able to be held accountable and to answer for your accountability

## Slide 21: Internal Control
Risk management is 1 way of establishing internal control
The Board is responsible for determining the nature and extent of the significant risks it is willing to take in achieving it’s strategic objectives
They should maintain sound risk management and internal control systems and review the effectiveness of these at least annually.
Notes: Other controls are Financial, Operational and Compliance

## Slide 22: The M_o_R framework
Fig. 1.1
Identify
Assess
Plan
Implement
Communicate
M_o_R Approach
Risk Register
M_o_R Approach
Risk Management
Policy
M_o_R Approach
Risk Management
Process Guide
M_o_R Approach
Issue Log
M_o_R Approach
Risk Management
Strategy
Management of Risk Principles
Embed and Review
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Notes: Risk Management

## Slide 23: M_o_R principles
Informed by corporate governance principles and the international standard for risk management ISO 31000: 2009
High level universally applicable
To help design an appropriate approach to risk management as part of the internal controls

## Slide 24: The 7 +1 M_o_R principles
Aligns with objectives
Fits the context
Engages stakeholders
Provides clear guidance
Informs decision-making
Facilitates continual improvement
Creates a supportive culture
Achieves measurable value
Notes: The first 7 are enablers, the final one is the result of implementing risk management well.
Relationship of these principles to the 12 from the 2007 guidance:
Aligns with objectives = Organisational Objectives
Fits the context = Organisational Context
Engages stakeholders = Stakeholder Involvement
Provides clear guidance = M_o_R Approach, EWI’s and Roles & responsibilities
Informs decision-making = Roles and Responsibilities, Reporting and EWI’s
Facilitates continual improvement = Continual Improvement and review cycle
Creates a supportive culture = Supportive Culture, overcoming barriers to M_o_R and Support structure
Achieves measurable value = builds upon Embedding and reviewing

## Slide 25: The M_o_R Process
Identify
Implement
Communicate
Assess
Plan
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Notes: The M_o_R Process

## Slide 26: The M_o_R process
Fig. 4.2
Identify:
context
identify the risks
Assess:
estimate
evaluate
Plan
Implement
Communicate
M_o_R process
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 27: The M_o_R Approach
Fig 1.1
M_o_R Approach
Risk Register
M_o_R Approach
Risk Management
Policy
M_o_R Approach
Risk Management
Process Guide
M_o_R Approach
Issue Register
M_o_R Approach
Risk Management
Strategy
© Crown Copyright 2010. Reproduced under licence from AXELOS Ltd.
Notes: Risk Management
Explain that we will address the documents later on in the day and on day 2.

## Slide 28: M_o_R approach
Risk management policy – How risk management will be implemented throughout an organisation
Risk management process guide – All the steps (Identify  Assess  Plan  Implement) and communication therein
Risk management strategies – The specific risk management activities that will be undertaken

## Slide 29: M_o_R approach support documents
Records
Risk register
Issue register
Plans
Risk improvement plan
Risk communications plan
Risk response plan
Reports
Risk progress report

## Slide 30: Relationship between documents
Policy
Process guide
Strategy
Risk response plan
Risk register
Risk communications plan
Risk improvement plan
Issue register
Risk progress report
For the organization
For each organizational activity, e.g. operation or programme
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Notes: Take note of the error in the book. Rename risk progress plan to report.

## Slide 31: Embedding and Reviewing
Fig. 1.1
Embed and Review
© Crown Copyright 2010 Reproduced under licence from AXELOS Ltd.
Notes: Risk Management

## Slide 32: Embedding and Reviewing M_o_R
Objectives
To show the importance of integrating risk management into the culture of the organisation
To explain how this can be achieved
To highlight the need for regular reviews to ensure risk management is being appropriately and successfully handled across the organisation
Ref. 5.1
Notes: Embedding and Reviewing M_o_R – Objectives

## Slide 33: Now the Practitioner level
Notes: Participants will take the M_o_R foundation sample paper 1.
Let them check their answer and explain which Syllabus area still needs improving.

## Slide 34: The M_o_R framework
Identify
Assess
Plan
Implement
Communicate
M_o_R Approach
Risk Register
M_o_R Approach
Risk Management
Policy
M_o_R Approach
Risk Management
Process Guide
M_o_R Approach
Issue Log
M_o_R Approach
Risk Management
Strategy
Management of Risk Principles
Embed and Review
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 35: The M_o_R principles
Aligns with objectives
Fits the context
Engages stakeholders
Provides clear guidance
Informs decision-making
Facilitates continual improvement
Creates a supportive culture
Achieves measurable value

## Slide 36: Aligns with objectives
The primary outcome:
Suitable risks are identified
Appropriate priority for action is given to:
    The individual risks
    The overall risk associated to the objective
Ref. 2.2
Risk management aligns continually with organizational objectives

## Slide 37: Aligns with objectives
The purpose of risk management is to support an organization securing its objectives
Risk identification should not be commenced until the objectives of the organizational activity are clearly understood
When objectives are changed the previously identified risks should be reviewed and updated
Ref. 2.2
Notes: Added slide

## Slide 38: Risk appetite and capacity
Risk appetite – the unique attitude towards risk taking
Risk appetite is a function of the organisation’s ‘capacity’ to bear risk
Risk capacity is an organisation’s ability to absorb risk
Board and senior management responsible for defining after determining its risk bearing capacity
Part of risk governance and internal controls
Ref. 2.2

## Slide 39: The perspectives
Aligns with objectives at
Strategic
Programme
Project and
Operational
perspective

## Slide 40: Strategic perspective
Concerned with achieving desired outcomes by defending or changing organisational performance
Usually a mixture of:
  Financial - tangible measures satisfying stakeholder or shareholder expectations
  Core service: relating to increasing efficiency, quality or output
  Stakeholder or customer - ensuring reputation is managed and demand for services remains strong and predictable
  Organisational capability - ensuring that the organisation remains relevant and able to meet future needs (e.g. innovation and new service development)
  Resource - ensuring staff and suppliers are providing the skills and commodities required by the organisation
Aligns with objectives

## Slide 41: Programme perspective
Concerned with achieving desired outcomes by step change improvements to organisational performance
Benefits:
  Measurable improvement of value linked to strategic level key performance indicators where possible
  Tangible or intangible
  May be expressed in financial or non-financial terms
Capability:
  New capability, enhanced existing capability, or removal of a capability that is no longer desired
  Capability objectives affect the operational performance of the organisation
  Mapped to projects within the programme that deliver the change
Aligns with objectives

## Slide 42: Project perspective
To inform decision-making during project selection and definition
To improve project performance during design and delivery so that completed projects lead to enhanced organisational performance
Tend to include:
  Time (e.g. delivery by a specified date)
  Cost (e.g. delivery on budget or delivery without penalties from contractors)
  Quality
  Scope
Aligns with objectives

## Slide 43: Operational perspective
Concerned with day-to-day management of the organisation. It should consider:
  Reputation
  Volume (e.g. customers or units produced)
  Cost (e.g. per unit produced)
  Quality (e.g. unit or process failures)
  Internal control (e.g. health, safety or failure)
  Revenue
  Staff (e.g. satisfaction)
  Customer (e.g. churn, satisfaction)
Aligns with objectives

## Slide 44: The M_o_R principles
Aligns with objectives
Fits the context
Engages stakeholders
Provides clear guidance
Informs decision-making
Facilitates continual improvement
Creates a supportive culture
Achieves measurable value

## Slide 45: Fits the context
If you don’t know what the context is:
You don’t know what the world around you looks like
You don’t realise you’re part of something bigger
It’s less likely you’ll find all relevant stakeholders
It is less likely you will find the important risks
Risk identification is not effective and efficient
There is less chance of being successful
Ref. 2.3

## Slide 46: Fits the context
The primary outcome of an approach that fits the context is:
Money is not wasted
    On oversizing
    Or on inability to cope with the risks within the risk capacity and appetite
Ref. 2.3
Risk management is designed to fit the current context

## Slide 47: Fits the context
Context is a primary source of risk
Private sector: external organisations who can impose policies, pricing restrictions, fines etc
Public sector: disparate subjects of policies, politics, the economy, technological change etc
Risk Manager must be familiar with the context to challenge the risk identification and assessment
Context will influence organisation’s risk appetite
Ref. 2.3
Notes: Added slide
Organisations should have the ability and capacity to respond to changes in the business environment (external)
The capacity to understand immediate threats and opportunities and those on the horizon (slowly gaining in clarity) is a measure of its ability to compete.

## Slide 48: Fits the context of M_o_R
Fig. 1.2
Long-term
Medium-term
Short-term
B
u
s
i
n
e
s
s
C
h
a
n
g
e
Strategic
Programme
Project
Operational
Long term goals, sets the context for decisions at other levels.
Risks may not become apparent until well into the future, therefore should be reviewed on a regular basis.
Programmes and projects bring about business change.
Decisions relating to medium-term goals are narrower in scope than strategic ones, particularly in terms of timeframe and financial responsibilities.
Emphasis is on short-term goals to ensure ongoing continuity of business services
Decisions about risk at this level must also support the achievement of long- and medium-term goals.
Where & When to apply risk management
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 49: Inter-relationships perspectives
Fig. 6.1
Strategic risks
Programme
risks
Project
risks
Operational
risks
Change
management
objectives
Day-to-day
management
objectives
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 50: Enterprise risk management (ERM)
Seeks to understand the relationships between the risks across the strategic, operational, programme and project perspectives
To ensure the overall amount of risk taken fits the capacity of the organization
ERM helps determine the optimal blend of responses to risks

## Slide 51: The perspectives
Fits the context at
Strategic
Programme
Project and
Operational
perspective
Notes: Looking at the organizational context from the different perspectives
A cross-reference of the principles and the perspectives

## Slide 52: Strategic perspective
Strategic risks are concerned with ensuring overall business success, vitality and viability
Impacts executive level decision-making whilst considering the organisation’s external environment and other organisations that work with or against it
Ref. 6.2
Fits the context
Notes: Examples,
Traffic Jams / Commuting
Environmental Issues
People Planet Profit
Work-life balance
Impact of Social media

## Slide 53: Strategic areas of uncertainty
Extent of competition
Reorganizations
Stakeholders perceptions relating to reputation
Changes to legislature
Macro-economic changes
Political and market factors
New technologies
Critical incidents and force majeur
Notes: This list is taken from chapter 6.2.2

## Slide 54: Programme perspective
Focuses on significant change to the organisation relative to other changes and the ongoing operations of the organisation
Risks concerned with transforming business strategy into new ways of working that deliver measurable benefits to the organisation
Threat and opportunity ‘trade-offs’ involved become even more complex as projects compete with one another for resources
Ref. 6.3
Fits the context
Notes: Examples:
Flexible workforce
Flexible ways of working together, WAT Working Apart Together

## Slide 55: Programme areas of uncertainty
Clarity of expected benefits
Changes in priorities or objectives
Delegated strategic risks
Working across organizational boundaries
Funding
Quality of the project outputs
Impact on the business-as-usual
Notes: This list is taken from chapter 6.3.2

## Slide 56: Project perspective
Focuses on the successful delivery of a predefined output or product capable of achieving business benefits
Project risks are concerned with delivering defined outputs to agreed quality within agreed:
  Time
  Cost
  Scope
Ref. 6.4
Fits the context
Notes: Examples:
Too many projects going on at the same time
Third party which is not flexible enough
Third party which is reorganizing it’s business
Solution which is not sustainable (green)

## Slide 57: Project areas of uncertainty
Availability of skills an key resources
Clarity of customer requirements
Strength of control and change management process
Procurement
Quality of project infrastructure
Scheduling of deliverables
Notes: This list is taken from chapter 6.4.2

## Slide 58: Operational perspective
Concerned with maintaining an appropriate level of business service to existing and new customers
Focuses on the people, processes, and technologies that support ongoing BAU or service delivery activities in relation to customer expectations
Includes services delivered to internal or external customers
Operations must monitor how strategic changes affect ongoing BAU and service delivery activities
Customers receiving the affected business service will recognise the appearance of operational risks
Ref. 6.5
Fits the context
Notes: Business As Usual – BAU
Examples:
To many changes happening at the same time
Legislation changing, new demands from regulations

## Slide 59: Operational areas of uncertainty
Strength of cost and quality controls
Clarity of service requirements
Quality of the necessary infrastructure
Strength of contracts
Changes to service requirements
Product development
Incident handling
Business continuity
Infrastructure investments
Legal and contractual obligations
Notes: This list is taken from chapter 6.5.2

## Slide 60: Operational controls
Must establish a framework of operational controls
Ensures that the operational aspects of the organisation are conducted in an appropriate manner and the correct checks and balances are in place
Examples of controls:
  multiple signatures for cheques
  different authorisation levels for expenditure
  credit/trade vetting of suppliers and customers
  adherence to specific standards
Assurance team including internal/external audit will review the controls and there effectiveness
Ref. 6.5
Fits the context
Notes: Operational Controls

## Slide 61: The M_o_R principles
Aligns with objectives
Fits the context
Engages stakeholders
Provides clear guidance
Informs decision-making
Facilitates continual improvement
Creates a supportive culture
Achieves measurable value

## Slide 62: Engages stakeholders
The primary outcome is:
The risk identification process is thorough
The difference are understood and resolved if possible
So that time and money is not wasted on misunderstandings that could have been avoided
Ref. 2.4
Risk management engages stakeholders and deals with different perceptions of risk

## Slide 63: Engages stakeholders
All major stakeholders need to be identified and engaged
Provide information detailing what will be the impact on them
Sponsoring stakeholder’s objective should be captured and discussed
Proactive and early involvement engenders support, acceptance and collective ownership
It is important to manage stakeholder expectations so that unrealistic objectives are avoided
Ref. 2.4
Notes: When appropriate stakeholders should be involved in the identification and assessment of risks
Stakeholders may have to take responsibility for risk events that materialize

## Slide 64: Engages stakeholders
Stakeholder
‘Any individual, group or organization that can affect, be affected by, or perceive itself to be affected by, an initiative (programme, project, activity or risk).’
Where to look
Owners or shareholders, executive management, operational management and staff of the organisation(s),
Customers or consumers,
Internal/external audit,
Security
Political or regulatory bodies
Trade Unions,
General public
Ref. 2.4

## Slide 65: The perspectives
Engage stakeholders at
Strategic
Programme
Project and
Operational
perspective

## Slide 66: Strategic perspective
Owners or shareholders, investors or funders
Key customers or customer groups
Political, legal or regulatory bodies
The wider community in which the affected organisation exists, such as the general public
Strategic partners or suppliers
Employees
Engages stakeholders

## Slide 67: Programme perspective
Programmes focus on delivering benefits to the organisation and often affect stakeholders from many different internal and external organisational units
Risk management for a programme must be designed to work across appropriate organisational boundaries in order to accommodate and engage stakeholders
Engages stakeholders

## Slide 68: Programme perspective
Owners or shareholders, executive management, operational management
Programme sponsor
Anyone with a vested interest in the success of the programme
Key beneficiaries
Suppliers
Customers or consumers affected by the outcome
Internal and/or external audit / Security
Trade unions
Political or regulatory bodies
The wider community (general public)
Programme/Project management teams
Engages stakeholders
Notes: Someone with a vested interest has a personal stake, he/she will benefit directly and personally from it

## Slide 69: Project perspective
  Internal and external suppliers
  Customers or recipients of project deliverables
  Political or regulatory bodies
  Project sponsors
  Management
  Team members
Engages stakeholders

## Slide 70: Operational perspective
Owners or shareholders, executive/operational management
Staff responsible for:
  The delivery of products/services activities supporting the delivery of products/services
  Implementing, maintaining and monitoring internal controls
  Supplying goods or services to the department or organisation
Customers or consumers affected by the services/products
Business partners and suppliers
Engages stakeholders

## Slide 71: Operational perspective
Other departments, divisions or offices
Internal and/or external audit
Compliance departments
Stakeholders involved in Security, Health & Safety and Business continuity
Trade unions
Political or regulatory bodies
Project and programme management teams delivering projects and programmes
The wider community in which the affected organisation exists, such as the general public
Engages stakeholders
Notes: This is just an example
Check what techniques might be used to speedup this process and be more complete (Prompt lists, lessons learned)

## Slide 72: The M_o_R principles
Aligns with objectives
Fits the context
Engages stakeholders
Provides clear guidance
Informs decision-making
Facilitates continual improvement
Creates a supportive culture
Achieves measurable value

## Slide 73: Provides clear guidance
The primary outcome is:
Consistency in the application of risk management
That the organization can compare results with plans
Judge whether resources are being deployed optimally
Ref. 2.5
Risk management provides clear and coherent guidance for stakeholders
Notes: Relate these to the approach documents and having

## Slide 74: Provides clear guidance
The policies, strategies and plans should describe which activities should be routinely subject to risk Identification, assessment and control.
Risk policies should state the risk appetite and capacity (ability to absorb risks).
Risks should be assessed in a way that enables risk management action to be prioritized and to be effective as possible
There is no ‘one-size-fits-all’ risk management solution. Policies, strategies and plans should be tailored to suit the circumstances
Ref. 2.5
Notes: Successful risk taking should be a combination of maximisation of opportunities and mitigation of threats associated with those opportunities
The selected approach should be adopted for all processes and reporting to ensure the adoption of best practices and ease of amalgamating information
(info put together)
Risk management should be integrated with other disciplines when implemented, to support improvements in programme and project management and other business processes.

## Slide 75: Roles and responsibilities
Clear roles and responsibilities for the management of risk established
Board is instrumental in providing leadership and direction for this task
‘Centre of Excellence’ and dedicated resource are a prerequisite for the successful delivery of risk management
Ref. 2.5

## Slide 76: M_o_R approach main documents
Risk management policy – How risk management will be implemented throughout an organisation
Risk management process guide – All the steps (Identify  assess  plan  implement) and communication therein
Risk management strategies – The specific risk management activities that will be undertaken
Ref. 2.5

## Slide 77: The perspectives
Provides clear guidance at
Strategic
Programme
Project and
Operational
perspective

## Slide 78: Strategic perspective
Risk management for the strategic perspective should be shaped by the:
  Risk management policy
  Strategic risk management strategy
  Risk management process guide
The risk management strategy defines how management of risk will be handled by the
  Accounting officer or CEO (who also checks its existence)
  Executive management team and management board
Ref. 6.2.4
Provides clear guidance

## Slide 79: Programme perspective
Risk management for the programme perspective should be shaped by the
  Risk management policy
  Programme risk management strategy
  Risk management process guide
The risk management strategy will define how the management of risk will be handled by the
  Senior Responsible Owner
  Programme Director/Manager
  Programme Board
Ref. 6.3.4
Provides clear guidance

## Slide 80: Project perspective
Risk management for the project perspective should be shaped by the:
  Risk management policy
  Project risk management strategy
  Risk management process guide
  it may also be influenced by the programme risk management strategy where the project forms part of a programme
The risk management strategy will define how the management of risk will be handled during the lifetime of the project by the
  (Possibly) Programme Director/Manager
  Project Board (Executive) and Project Manager
Ref. 6.4.4
Provides clear guidance

## Slide 81: Operational perspective
Risk management for the operational perspective should be shaped by the:
  Risk management policy
  Operational risk management strategy
  Risk management process guide
The risk management strategy defines how risk management will be handled during the lifetime of the operational unit or service
Operational risk management strategy is used to show close links to security, health & safety, business continuity and contingency planning
Ref. 6.5.4
Provides clear guidance

## Slide 82: The M_o_R principles
Aligns with objectives
Fits the context
Engages stakeholders
Provides clear guidance
Informs decision-making
Facilitates continual improvement
Creates a supportive culture
Achieves measurable value

## Slide 83: Informs decision-making
The primary outcome is:
Important decisions are taken with explicit consideration for risks
A safeguard for good decision-making (and decision-outcomes)
Ref. 2.6
Risk management is linked to and informs decision-making across the organization

## Slide 84: Informs decision-making
KPI’s and EWI’s are established for critical business systems
Decision-makers with the authority to take corrective actions, examine the indicators on a regular basis
Information is presented concise and consistent so that it can be really understood
If business or context changes the indicators are revised
Not only looking forward but also measure changes in the organizational environment
Ref. 2.6
Notes: Greater granularity (=level of details) is added to the indicators where additional information will aid decision-making
Reports on trend information on the indicators are kept confidential. This is sensitive information about the organisation.

## Slide 85: KPI’s
KPI’s are established for the business to:
To help define and evaluate success in achieving organisational objectives and business benefits
Often relate to level of service excellence
EWI’s ultimately relate to KPI’s
Ref. 2.6

## Slide 86: EWI’s
Aim to be proactive and anticipate potential problems
EWI’s:
  Established for critical business activities to provide information on the potential sources of risk
  Can track business sensitive issues - if certain predefined levels are reached, corrective action will be triggered
  Applied to issues such as staff turnover, liquidity, absenteeism, sickness, sales, stock levels, loss of customers, supplier default, late payments, success rate of tenders, overhead costs and revenues
  Must measure critical business activities and be reviewed on a regular basis
Information must be accurate, passed to decision-makers and acted on
Ref. 2.6

## Slide 87: The perspectives
Informs decision-making at
Strategic
Programme
Project and
Operational
perspective

## Slide 88: Strategic perspective
Key EWI’s relate directly to corporate objectives e.g.:
  Finance-related: turnover, profitability, operating costs, liquidity and capital expenditure
  Customer-related: market share, customer satisfaction and bid loss
  Growth-related: new product development and project failure or success
  Employee-related: turnover and satisfaction
  Supplier related: contract penalties and insurance premium increases
  Third-party-related: insurance premiums, legal action, media coverage and regulator penalties
  Other Early Warning Indicators can be found in change in the organisation’s context (PESTLE)
Informs decision-making
Notes: To help you remember a mnemonic: FC GESTO

## Slide 89: Strategic perspective
Regular risk reports should be provided to the Accounting Officer/CEO and Executive Management Team
Additional reports for key decisions and at the start of a planning cycle
Prompt reporting of risks exceeding tolerance thresholds
Facilitate escalation of programme and project and operational risks
Facilitate delegation of risk when they decline
Don’t forget reporting responsibilities to stakeholders
Informs decision-making
Notes: Reporting

## Slide 90: Programme perspective
Relate directly to programme objectives and will be selected for their relevance to the programme
EWI’s here might include:
  Establishment of new capabilities on time and on budget
  Delivery of planned benefits on time and on budget
Other Early Warning Indicators are changes in the programme’s context (e.g. management structures, stakeholders and interdependencies with other programmes)
Informs decision-making
Notes: Early warning indicators

## Slide 91: Programme perspective
Regular programme risk reports should be provided to the Senior Responsible Owner and programme director/manager
Risk reports produced at key decision points (end of programme definition or end of each tranche )
Risks exceeding tolerances require prompt reporting to the Senior Responsible Owner and programme board
Programme risks escalated to the strategic perspective where they exceed the risk tolerance set for the programme within the programme’s risk management strategy
Project risks escalated to the programme where they exceed tolerances or where they could affect the achievement of programme objectives
Informs decision-making
Notes: Reporting

## Slide 92: Project perspective
Key EWI’s relate directly to the project’s objectives
EWI’s here might include:
  Design packages accomplished to schedule/late
  Approvals accomplished to schedule/late
  Major supplier performance
  Contractor performance
  Adherence to schedule
  Staff turnover
  Claims submitted
  Stoppages
  Increases in staff skills, motivation, morale or loyalty
Informs decision-making
Notes: Early warning indicators

## Slide 93: Project perspective
Objectives of project EWI’s:
Provide information to enable corrective or mitigation actions to take place
Indicators must be updated on a regular cycle and any action thought appropriate must be implemented swiftly to ensure it will have an impact
Project participants must know from the start
  What the indicators are
  What information is to be collected to be conveyed against the indicator
  Reporting frequency
  Corrective action will be required when necessary to implement project changes to achieve the project objectives
Informs decision-making
Notes: Early warning Indicators

## Slide 94: Project perspective
Regular project risk reports should be provided to the Senior Responsible Owner and project director/manager.
Risk reports produced at key decision points i.e project initiation and stage end
Updates required as project progresses
Sponsors need a detailed progress report at key stages to enable them to decide if they wish to continue, suspend or terminate the project
Informs decision-making

## Slide 95: Operational perspective
Relate directly to:
Customer churn
Staff turnover
Levels of overtime of staff
Achievement of service quality levels
Achievement of unit cost targets
Achievement of volume targets
Achievement of delivery on time targets
Achievement of revenue targets
Levels of safety incidents or injury
Incidents of plant or process failure
Informs decision-making
Notes: Early Warning Indicators

## Slide 96: Operational perspective
Regular reviews by operational management and independent personnel against operational controls
All staff should be responsible for reporting breaches in internal controls
Identified risks should be recorded and escalated to management for assessment, and control
If exceeding the tolerance levels, further escalation or notification to senior management is required
Management team should provide any exception reports if necessary
Informs decision-making
Notes: Reporting

## Slide 97: The M_o_R principles
Aligns with objectives
Fits the context
Engages stakeholders
Provides clear guidance
Informs decision-making
Facilitates continual improvement
Creates a supportive culture
Achieves measurable value

## Slide 98: Facilitates continual improvement
The primary outcome is:
That valuable resources are not wasted by making the same mistake twice
Or by missing an opportunity
Ref. 2.7
Risk management uses historical data and facilitates learning and continual improvement

## Slide 99: Facilitates continual improvement
For continual improvement an organisation should:
Develop strategies to improve risk maturity
Review against a maturity model to determine the expected benefits
Prepare a realistic plan to the next level of maturity
Manage it as a project with clear objectives, resources, timeframe and against a Business case
Reviews will help an organisation understand the effectiveness of risk response planning
Perform M_o_R health checks
Ref. 2.7
Notes: Added slide

## Slide 100: Facilitates continual improvement
How ‘mature’ is your organisation?
App. D
Optimising
Managed
Defined
Repeatable
Initial
Maturity models help develop strategies to improve risk maturity
Notes: Refer to the appendix C and D and to the topic of Embedding and reviewing which will be dealt with on day 3

## Slide 101: The M_o_R principles
Aligns with objectives
Fits the context
Engages stakeholders
Provides clear guidance
Informs decision-making
Facilitates continual improvement
Creates a supportive culture
Achieves measurable value

## Slide 102: Creates a supportive culture
The primary outcome is:
The organisation can attain the full value of risk management
1 + 1 = 3
Ref. 2.8
Risk management creates a culture that recognizes uncertainty and supports considered risk-taking

## Slide 103: Creates a supportive culture
Culture is ‘ the way things are done’
The way things are done should be supportive to risk management in the organisation
Varies from doing just enough to driving business improvement
Described in roles and responsibilities
The culture will be embodied by the policy documents, move away from ‘tick-box’ compliancy
No blame
Walk the walk and talk the talk
Attain full value from its investment in risk management
Ref. 2.8
Notes: More is covered during day three when Embedding and reviewing is covered
7 Embedding and Reviewing cultural components
Helping your memory with a mnemonic ABC BORS
Awareness, Behavior, Commitment,
Benefits, Opportunities, Roles & Responsibilities, Success factors

## Slide 104: Risk appetite
Risk neutral – the ideal, comfortable with the decision making process, deliberate, proportionately aligns mitigation measures with risks and opportunities
Risk averse Actively avoid risks, afraid, worrying, less willing to try new activities
Risk tolerant
is relaxed with uncertainty, head in the sand, prefers ‘Ignore’ as a mitigation approach
Risk seeking Like to take risks, tries new activities, overly optimistic, likes a challenge, under estimates the dangers
Afgeleid van interview van Janice Preston (PMI Podcast http://www.thepmpodcast.com/index.php?option=com_content&task=view&id=110&Itemid=9/ )
Únderstanding and Managing Risk Attitude: David Hillson and Ruth Murray-Webster (ISBN: 978-0-566-08798-1)
Notes: Afgeleid van interview van Janice Preston (PMI Podcast http://www.thepmpodcast.com/index.php?option=com_content&task=view&id=110&Itemid=9/ )
Drie niveau’s zijn een continuum
Gaat er niet om WAAR je staat, dat kan erg afhangen van de AARD van je bedrijf
Gaat om Welke houding en gedrag je aanneemt – Neutraal
Aanrader:
Únderstanding and Managing Risk Attitude: David Hillson and Ruth Murray-Webster
ISBN: 978-0-566-08798-1

## Slide 105: Risk neutral core quadrants
Reckless
Unthinking, foolish, headless chicken, cowboy, act on a whim, over excited
Pitfall
Entrepreneur
Courageous, progressive, proactive, driving, energetic, researching, adventurous, exciting
Quality
Cautious
Conservative, pragmatic, careful, controlled, safe, trustworthy, (continuity, availability)
Challenge
Rigid (indolence)
Afraid, idle, inactive, overly conservative, put off, indecisive, avoidance behavior, slacker
Alergy

## Slide 106: Appreciate each others quality
Reckless
Entrepreneurial
Cautious
Allergy
Pit fall
Quality
Challenge
Rigid
Notes: Een tevreden klant / medewerker is een blije medewerker.
Onderzoek naar hapiness

## Slide 107: The M_o_R Principles
Aligns with Objectives
Fits the context
Engages stakeholders
Provides Clear Guidance
Informs decision-making
Facilitates continual improvement
Creates a supportive culture
Achieves measurable value

## Slide 108: Achieving measurable value
Performance measures like:
Reduction in waste
Increase in satisfaction
Improved regulatory performance
Process measures like:
Reduction in surprises
Increase in participation
Increase in visibility
Better forecasting
Ref. 2.8
Risk management enables achievement of measurable organizational value
Notes: Make the link with MoV for more in-depth guidance

## Slide 109: Achieving measurable value
Performance measures like:
Reduction in waste
Increase in satisfaction
Improved regulatory performance
Process measures like:
Reduction in surprises
Increase in participation
Increase in visibility
Ref. 6.6

## Slide 110: Integrating RM across perspectives
Encompasses all areas of organisational exposure to risk
Prioritise and manage those exposures as a portfolio
Evaluate the portfolio holisticly
Recognise combined exposure is not the same as the sum of all exposures
Ref. 6.7

## Slide 111: Controls for managing across perspectives
A mechanism for passing risks across boundaries to be managed at the most suitable level
Effective escallation, delegation and communication between perspectives
And clearly described roles and responsibilities
Ref. 6.7

## Slide 112: Roles and Responsibilities
Senior team
Board, executive team, steering group, sponsoring group
Senior manager appointed as representative
Sponsor, SRO, Executive, Accounting Officer or CEO
Manager
Risk manager, programme manager, project manager, operational manager, or other line manager
Assurance
Internal Audit Department, portfolio, programme or project office or a central risk function
Risk Specialists
Risk practitioner, risk coordinator or risk facilitator
Team
Participants, project and programme team members, all Staff
Table 6.1
Notes: Refer to table 6.1 and the hierarchy of responsibilities to make RM work

## Slide 113: The M_o_R Framework
Identify
Assess
Plan
Implement
Communicate
M_o_R Approach
Risk Register
M_o_R Approach
Risk Management
Policy
M_o_R Approach
Risk Management
Process Guide
M_o_R Approach
Issue Log
M_o_R Approach
Risk Management
Strategy
Management of Risk Principles
Embed and Review
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 114: The M_o_R Approach
The Risk Management Policy
The Risk Management Process Guide
The Risk Management Strategies

## Slide 115: Developing the Policy
Policy must be written, reviewed and subsequently signed off by a member of the board or the audit committee
Requires confirmation that the recipient has received, read and understood the content
Must be updated on a regular basis and their application needs to be monitored
Special attention paid to communicating the benefits of risk management with examples
Must show relationship to the principles

## Slide 116: Risk Management Policy: Purpose
Communicates how risk management will be implemented throughout an organisation (or part of an organisation) to support the realisation of its strategic objectives
Small organisations - single policy, Larger organisations - a hierarchy of policies
Communicates why risk management should be undertaken
Provides a common language and uniformity across risk management processes
Removes ambiguity about the organisation’s risk appetite and escalation rules
Describes the format, timing and content of reports
Can describe the financial benefits of risk management
Can include a budget for risk management
Detailed or high-level description of the risk management process
Ref. 3.2 App. A.1

## Slide 117: Risk Management Policy: Composition
Introduction
Risk appetite and capacity
Risk tolerance thresholds
Procedure for escalation and delegation
Roles and responsibilities
Glossary of terms
Risk management process
KPI’s and EWI’s
When risk management should be implemented
Ref. 3.2 App. A.1
Reporting
Budget
Quality assurance
Annual review

## Slide 118: Benefits of Defining Risk Appetite
Aids understanding of the relative significance of the risks faced by the organisation
Sets policy for considering and approving levels of risk taking
Helps prioritise risk management activities
Aids more efficient allocation of capital
Better ‘insulation’ against any shock to future earnings
Helps allocate resources appropriately
Allows for creativity within acceptable limits
Reduce the possibility of exposure to exceeding capacity
Helps make better decisions

## Slide 119: Risk tolerance thresholds
Risk tolerance thresholds (levels of exposure) first created within business units
If exceeded - must be escalated
Must get senior management buy-in
Management considers interprets and decides on threshold limits for their units and function(s)
Costs of establishing thresholds include:
  Board and senior management time
  IT staff time – supporting risk management activities
  Central risk management team time
  Internal audit/external consultants time

## Slide 120: Procedure for Escalation
Risk escalation procedure developed for each perspective
Management teams then advised of the tolerance thresholds
If risk(s) exceeds threshold - results are escalated to a senior manager
Senior manager decides on a course of action or escalates to a more senior level
Thresholds are commonly financial but may relate to other success criteria such as:
  Timeframe
  Operational requirements
  Regulatory compliance matters
Notes: Escalation Procedures
For each perspective (or major activity), a risk escalation procedure should be developed whereby management teams (at these perspectives) are advised of the tolerance thresholds (see above) to which they are required to adhere.

## Slide 121: When to Implement
policy may describe the activities that require risk management
degree activity will varies according to the organisational perspective
explains when and how risk management should be applied throughout an organisation
detail for different perspectives – contained in Chapter 6

## Slide 122: Budget
No hard and fast rules to determine a budget for risk management
Budget correlated to the board’s or senior management’s perception of the value of risk management and its contribution to bottom-line performance

## Slide 123: Triggers for increase in Risk Budget
When:
Organisation suffers a major financial loss
The organisation has had its reputation tarnished
The regulatory regime has tightened
The regulator has imposed a fine
Hedging has been unsuccessful
A contract failed and penalties were imposed
A major shareholder raises concerns
A major programme or project has overrun
The Market becomes more competitive and margins erodes
Notes: A typical list from the Guidance that might have questions raised about it. There should be no doubt about the validity of any of the bullets.

## Slide 124: Quality Assurance & Review
Document and version control
Risk management practices reviewed at least annually
Following the review, actions should be undertaken to put in place planned improvements
Internal audit committee commonly review by:
  interviewing the central risk function and senior management
  reviewing risk management documentation

## Slide 125: Relationship with Other Policies
If the policy is one of a hierarchical set of policies, related policies:
  do not contain conflicting information
  roles and responsibilities unique to the policy are correct
  should be updated at the same time on a regular cycle
  should clearly explain the hierarchical relationship between the policies
  the reporting requirements within one policy must reflect and correlate with the reporting requirements in the other policies

## Slide 126: The M_o_R Approach
The Risk Management Policy
The Risk Management Process Guide
The Risk Management Strategies

## Slide 127: Risk Management Process Guide: Purpose
Describes the series of steps from Identify through to Implement
Must be tailored to the organisation
Should be applicable to all levels of management and activity
Describes a best practice approach
The audit committee, risk committee or risk function is normally responsible and determines the process that the organisation adopts
Used to review compliance against internal controls
Updated annually and always after the release of new national standards and new legislation
Ref. 3.3 App. A.2

## Slide 128: The Process Guide: Composition
Introduction
Roles and responsibilities
Steps in the process
Tools and techniques
Templates
Glossary of terms

## Slide 129: The Process Guide Roles & Responsibilities
Risk management process guide:
Who has overall responsibility for the process
The management structure for risk management
Who is responsible for updating the process
Who is responsible for risk management tools
The frequency that risk reviews are carried out

## Slide 130: The M_o_R Approach
The Risk Management Policy
The Risk Management Process Guide
The Risk Management Strategies

## Slide 131: Risk Management Strategy: Purpose
Describes the specific risk management activities that will be undertaken for a particular organisational activity
Typically prepared for a programme, project, office relocation, organisational change, outsourcing, a revision to key processes, or the introduction of new software
Tailored to each specific activity, whilst reflecting the process document and the hierarchy of policy documents
Should be prepared before embarking on any risk management activity
Where appropriate the strategy should relate to
  The Gateway Review Process for public sector programmes and projects
  Other assurance and approval processes for the private sector (e.g. RIBA Plan of Work)
Ref. 3.4 App. A.3

## Slide 132: Activities involved
Activity participants must understand why risk management information is required, (it helps when gathering information)
What is the sponsor is particularly interested in?
  the schedule?, choice of options? benefits of delivering early?
Success of strategy dictated by experience of staff
Needs sufficient resource to implement the strategy
The strategy must be coordinated with the:
  Risk Management Policy (or Policies)
  Risk Management Process Guide

## Slide 133: Timing of Activities
Risk Management Strategy record the lifecycle of the activity including the individual stages, review points and overall duration
Risk Management Strategy for projects or programmes will typically describe the risk management activities that will be carried out at each Stage or Gateway(or lifecycle review point)

## Slide 134: Risk Management Strategy: Composition
Introduction
Summary of the process
Tools and techniques
Records
Reporting
Roles and responsibilities
Scales of probability and impact
Risk Tolerance thresholds
Risk categories
Budget required
Templates
EWI’s for KPI’s
Timing of risk management activities
Glossary of terms

## Slide 135: The Process
Describes the risk management process with reference to the Risk Management Process Guide
States what departures (if any) have been made from the steps described in the process guide and why they were necessary
Alternatively it will state that the risk management process guide will be followed without exception
Notes: The Process
This section of the strategy will describe the risk management process that will be adopted and will refer to the Risk Management Process Guide.
It will state what departures (if any) have been made from the steps described in the process guide and why they were necessary, or it will state that the guide will be followed.

## Slide 136: Scales of Probability and Impact
Probability / impact grids developed specifically for each activity ensuring scales of cost and time (for instance) are relevant to the cost and timeframe associated with that specific activity
These grids should not be deemed final!
May be necessary to adjust the ranges to suit the circumstances as the risks and their impacts are identified and evolve

## Slide 137: Probability
Probability - the evaluated likelihood of a particular threat or opportunity actually happening
Includes consideration of the frequency with which this may arise
The pre-response/inherent probability initially assigned to a risk is based on no response action being in place
Once response actions are implemented it is likely that some post-response residual probability remains

## Slide 138: Impact
Impact is the result of a particular threat or opportunity actually occurring
The pre-mitigation impact initially assigned to a risk is based on no mitigation action being in place
Once mitigation actions are implemented there may some post-mitigation residual impact still remaining

## Slide 139: Examples of Impact Areas
Impacts on:
  costs
  timescale
  quality
  requirements
But could also be:
  reputation
  compliance
  maintainability
  accessibility
  reliability

## Slide 140: Expected Value
Equals the average Impact X probability percentage (where this is used)
This also is a pre-mitigation estimate and takes no account of any future risk management action to reduce the impact or the probability
Adding the expected values for all of the risks associated with an organisational activity, provides an understanding of the total risk exposure faced by that particular activity
However this figure represents the mean value and there is approximately a 50% chance that this figure will be exceeded
Table B.7

## Slide 141: Proximity
Risks are time based and are not constant
Severity of risk impact will vary according to when the risk materializes and triggers an issue
This time factor is known as the proximity of the risk
Probability and impact indicates the importance of a risk, proximity tells us its urgency
Knowing proximity helps identify the appropriate response and the required trigger and timing of the response

## Slide 142: The M_o_R - Records
The Risk Registers
The Issue Registers

## Slide 143: Risk Register: Purpose
Captures and maintains information on all of the identified threats and opportunities relating to a specific organizational activity
Each organization decides on the precise content of its own Risk Register
The layout of the register should reflect the sequence in which information is captured
Notes: Risk Register - Purpose

## Slide 144: Risk Register: Composition
Risk identifier
Risk category
Date raised
Raised by
Risk description
Probability
Impact
Expected value for each risk
Proximity
Risk response option
Risk response actions
Residual risk
Residual proximity
Secondary risks
Action status
Risk status
Risk owner
Risk actionee
For document management purposes the register should include:
a title (reflecting the organizational activity), date, date last updated, version number, author, file reference

## Slide 145: Risk Owner & Actionee
Owners- manages and controls all aspects of risks assigned to them
  Implementing actions to address the threats or to maximise the opportunities
  owners of the probability reduction actions may be different from those of the impact reduction actions
Actionees
  implements the risk response action or actions to respond to a particular risk or risks
  supports and takes direction from the risk owners

## Slide 146: Activities & Relationship
Risk Register must be maintained through all risk management steps and throughout the lifecycle of the organisational activity
Must be updated regularly and trend analysis should accompany updates of the register to check if the picture is improving or deteriorating
Activity objectives included so those involved in the identification remain focused on identifying risks to the objectives
Needs additional information being used for quantitative analysis
Notes: Activities & Relationship

## Slide 147: The M_o_R - Records
The Risk Registers
The Issue Registers

## Slide 148: Issues and Risks
Issue
Risk
Here, now
A certainty
Need to evaluate Impact
Urgency - needs immediate action
Possibility of re-occurrence results in a new risk
In the future
Uncertain
Need to evaluate Probability, Impact and Proximity
Time to plan - may or may not lead to action
Possibly raised as a consequence of existing issue
Ref. 3.6
Actions proactive and reactive
Actions reactive

## Slide 149: Issue Register
Captures and maintain information on all issues have already occurred and require action
May include risks that have materialised
Organisation decides precise content
Layout should reflect the sequence in which information is captured
Collects sufficient information to enable a timely and appropriate response to all issues
Risk Register and Issue Register should cross-reference
Notes: Issue log

## Slide 150: Issue Register: Composition
Issue identifier
Issue type (Rfc, Query, Off-spec, Problem, Concern, Benefit)
Date raised
Raised by
Issue description
Severity
Priority
Action required
Date action to be implemented
Action status
Issue owner
App. A.5
For document management purposes the register should include:
a title (reflecting the organizational activity), date, date last updated, version number, author, file reference
Notes: Also noted in Appendix A

## Slide 151: Activities & Relationship
Issue Registers record events that have already occurred - may require immediate attention
Needs to be a clear understanding of:
  the actual or potential scale of the impact
  what needs to be done and in what order
  what the timeframe is to be,
  the costs and
  which individuals will implement the response

## Slide 152: The M_o_R - Plans
Risk Improvement Plan
Risk Communication Plan
Risk Response plan

## Slide 153: Risk Improvement Plan
Once an approach to any cultural awareness programme has been agreed, a Risk Improvement Plan should be developed
Purpose:
  records current status of management of risk cultural awareness
  the behavioural targets that are to be achieved and an appropriate time period in which to achieve them
  the mechanisms/methods planned to be used to achieve the cultural change
App. A.6
Notes: Not to be confused with the Risk Response Plan that addresses the management of the responses to risks (Appendix A8)

## Slide 154: Composition
Current date
Category group
Existing behaviours
Target behaviour
Target date
Mechanisms
Measurement

## Slide 155: The M_o_R - Plans
Risk Improvement Plan
Risk Communication Plan
Risk Response plan

## Slide 156: The Risk Communications Plan
Relating to a specific activity:
Key elements of Information to be distributed
Roles and Responsibilities for communication
Stakeholders and their INFO need
How the information will be transferred
How feedback will be handled
Schedule of activities
App. A.7

## Slide 157: Communications plan: composition
Key elements of info to be distributed
Roles and responsibilities for communication
List of stakeholders and information requirements
Communication mechanisms
Process for handling feedback
Schedule of communication activities

## Slide 158: The M_o_R - Plans
Risk Improvement Plan
Risk Communication Plan
Risk Response plan

## Slide 159: Risk Reponse Plan
An extension of the risk register
Should be created and maintained by the risk owners
Typically includes:
Id, risk description(s)
Proximity and pre-response impact and probability
Risk owner and reponse plan (who, what, when, where)
Residual proximity, probability and impact
Response costs
App. A.8

## Slide 160: The M_o_R - Reports
Risk Progress report

## Slide 161: Risk Progress Report
Provide regular progress information to management on progress of planned actions and their effectiveness.
The progress report may be a separate report but could also be part of a wider progress report
As a minimum it should contain:
Trends of overall risk exposure
Numbers and trends of risks emerging in the different risk categories
Anticipated new risks that will require specific management attention

## Slide 162: M_o_R® Practitioner - Day 2

## Slide 163: The M_o_R Framework
Identify
Assess
Plan
Implement
Communicate
M_o_R Approach
Risk Register
M_o_R Approach
Risk Management
Policy
M_o_R Approach
Risk Management
Process Guide
M_o_R Approach
Issue Log
M_o_R Approach
Risk Management
Strategy
Management of Risk Principles
Embed and Review
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 164: The M_o_R Process
Identify
Implement
Communicate
Assess
Plan
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Notes: The M_o_R Process

## Slide 165: The M_o_R Process
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Notes: Focus on the two steps in Identify and assess
Relate the process to the Orange Book, explain what it is and how this might relate to a Dutch equivalent

## Slide 166: Communication throughout the Process
Carried out throughout the whole process
An organisation’s exposure to risk is never static
Effective communication key to the identification of new risks or changes in existing risks
Communication needed to provide assurance to third parties such as regulators, shareholders, stakeholders and staff that risks are being appropriately identified, assessed and controlled
Mediums for this are the annual review, statements of internal control and reports on planned activities such as investments, acquisitions and product development
Ref. 4.3

## Slide 167: Communication throughout the Process
Management must engage with staff to ensure:
  everyone understands appetite, policy, process, plans and regulatory requirements
  everyone understands the benefits
  each level of management, actively seeks and receives appropriate and regular assurance about the management of risk within their control
  the procurement team understands the requirement for making risk ownership explicit within contracts and service level agreements
  lessons learned are communicated
  no misunderstanding risk priorities

## Slide 168: The M_o_R Process Overview
Goals
Process step
Tasks
Outputs
Techniques
Inputs
Fig. 4.3
The key outcomes of the process.
The information produced by the process, then forms the inputs to the next process.
The risk management techniques that may be used to support the completion of the process.
Actions taken to transform the inputs into outputs, supported by the techniques and restricted by the barriers.
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 169: Identify – the Context
Ref. 4.4
Context
Regulatory framework
and corporate
governance requirements
Risk Management Policy
Risk Management
Process Guide
Activity Documents
Lessons Learned
SWOT analysis
PESTLE analysis
Stakeholder Analysis
Horizon scanning
Define the probability impact grid
Activity Analysis
Risk Management Strategy
Stakeholder Map
Lessons Learned
Techniques
Outputs
Inputs
Goals - To obtain information about….
The objectives of the activity
The scope of the activity and completeness of info
What assumptions have been made
What constraints are relevant
Stakeholders and their objectives
Activity fit relative to the organisational structure
The organisation’s own environment
The organisation’s approach to risk management
Identify
Assess
Plan
Implement
Communicate
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Notes: Identify – Step One Context

## Slide 170: Techniques for Identify - Context
Stakeholder analysis
  Help capture who the stakeholders are, their roles and degree of participation, Output is a stakeholder map
PESTLE analysis
  A wide-scan of the actual/potential problems that would affect objectives if not managed
SWOT analysis
  Focusing on attention on SWOT brings together the internal and eternal analysis, also SW can be cause for potential risks
Horizon scanning
  Systematic examination of emerging trends and future developments at the margins of current thinking and planning.
Defining the Probability and Impact grid
  It is important to be specific about the objectives (risk relevancy) and the impact scales (risk priority) , these are often used to articulate the risk tolerance threshold
Table B.1
Notes: Note:
Though these activities relate to the Process step ID the context, they are discussed here as the cross relation in the framework between Principles and the process are apparent. It also helps to clarify the objectives of the ID step in a wider framework.

## Slide 171: Stakeholder analysis
RACI diagram (also to support stakeholder analysis)
RACI-diagram is used to describe the roles and responsibilities of the participants in a business or project activity in terms of producing predetermined deliverables.
Responsible (those who undertake the activity, the resources)
Accountable (those who take the credit for success or responsibility for failure, the ‘activity manager’ – there must be at least one A specified for each activity)
Consulted (those whose opinions are sought)
Informed (those who are kept up-to-date on progress).

## Slide 172: RACI Diagram
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
A
B
C
D
E
R
A
C
C
C
1
2
3
4
5
C
A
I
C
R
R
A
I
I
C
R
I
A
C
C
R
I
C
A
C
Stakeholder
Activity
Responsible Accountable Consulted Informed
Notes: Can also be used during a stakeholder analysis
Verifies and Signs off can also be added

## Slide 173: Stakeholder Matrix
Stakeholders | Strategic direction | Financial | Operational changes | Interfaces with customers | Public safety | Competitive position
Business partner |  |  |  |  |  | 
Project teams |  |  |  |  |  | 
Customers |  |  |  |  |  | 
Press and media |  |  |  |  |  | 
Trade unions |  |  |  |  |  | 
Staff |  |  |  |  |  | 
Regulatory bodies |  |  |  |  |  | 
Interest

## Slide 174: Influence / interest Matrix
Fig. B.1
Low Medium High
Low Medium High
Key stakeholders need to accept the objectives
Stakeholders need to agree the translation of objectives into activities
Be kept informed of progress and remedies taken to achieve the objectives
Stakeholders notified of milestone completion
Potential impact of organisational activity on the stakeholders
Importance of the stakeholders to the organisational activity
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 175: PESTLE analysis
Politics
Suppliers
Local politics
Interest / lobby groups
The media
Economic
Funding Mechanisms
Internal funding models
Budgetary restrictions
Income targets
Social
Attitudes to education
Employment opportunities
Lifestyle changes
Mix of cultures
Technological
Current technologies
Emerging technologies
Legal
European &
National proposed & passed legislation
Environmental
Local, national & international impacts, outcomes of political and social factors

## Slide 176: SWOT analysis
Fig. B.3
Context analysis, e.g. using PESTLE
Strengths
Weaknesses
Opportunities
Threats
Positive
Negative
External
Internal
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 177: Enhanced SWOT analysis
Translate into tasks for the Activity Plan | STRENGTHS | WEAKNESSES
OPPORTUNITIES | How do I use these strengths to take advantage of the opportunities? | How do I overcome the weaknesses that prevent me taking advantage of the opportunities?
THREATS | How do I use my strengths to reduce the likelihood and impact of these threats? | How do I address the weaknesses that will make these threats a reality?
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 178: Probability / Impact Grid
Fig. B.4
0.9
0.36
0.18
0.09
0.045
Very High
71-90%
Impact
Very Low
Up to 10%
Low
11-30%
Medium
31-50%
High
51-70%
Very Low
0.005
0.015
0.025
0.035
0.01
0.03
0.05
0.07
0.02
0.06
0.01
0.14
0.04
0.12
0.20
0.28
0.08
0.24
0.40
0.56
0.72
0.7
0.5
0.3
0.1
0.05
Low
0.1
Medium
0.2
High
0.4
Very High
0.8
Probability
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 179: Identify - Identify the Risks
Ref. 4.5
Identify
the Risks
Activity Analysis
Risk Management Strategy
Stakeholder Map
Lessons Learned
Issues
Risk Checklist
Risk Prompt List
Cause and effect diagrams
Group techniques
Brainstorming
Nominal group
Delphi
Questionnaires
Individual interviews
Assumption analysis
Constraints analysis
Risk descriptions
Risk Register
Early Warning
Indicators for KPI’s
Techniques
Outputs
Inputs
Goals - To identify the risks to the organisation
that would reduce or remove the likelihood of
the organisation reaching its objectives
while maximising the opportunities that could
lead to improved performance.
Including:
Identifying the threats and opportunities to the activity
Preparing a Risk Register
Preparing key performance indicators and EWI’s
Understanding the stakeholders’ view of the risks
Identify
Assess
Plan
Implement
Communicate
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 180: Techniques for Identify - Identify the Risks
Risk Checklist
Risk Prompt list
Cause and Effect diagrams
Group techniques:
  Brainstorming
  Nominal Group Technique
  Delphi Technique
Risk Questionnaires
Individual interviews
Assumption analysis
Constraints analysis
Risk descriptions

## Slide 181: Checklists and Prompt lists
Risk Checklist
  Useful aids - they ensure that risks identified on previous similar activities are not overlooked for the current activity under examination
Risk Prompt list
  Categorises risks into types or areas
  Stimulates thinking about the sources of risk in the widest context.

## Slide 182: Cause and Effect diagram
Fig. B.6
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Third party
Poor representation in project
Misunderstanding over payment schedule
Payment outstanding for analysis work
Poor management of plan
Business analyst on holiday
Analysis data incomplete
Concern over development cycles for front-end panels
Technical
Estimates have no precedent in IS
User
Business
Insufficient user input
User requirements did not address archiving
Business requirement unclear
Project board unable to sign off
Concern over costs of developing archiving sub-system
Delay to functional specification sign off

## Slide 183: Risk Breakdown Structure
Fig. B.5
Project risk
Technical risk
Management risk
External risk
Commercial risk
Scope definition
Requirements definition
Technical processes
Technology
Technical interfaces
Technology scaling
Performance
Reliability, safety, security
Test and acceptance
Project management
Organization
Resourcing
Communication
Information
Health and safety environment
Corporate policy
Reputation
Contractual T & Cs
Financing
Liabilities and warranties
Payment terms
Suspension and termination
Internal procurement
Subcontracts
Client stability
Applicable law
Partner financial stability
Partner relevant experience
Legislation and regulatory
Exchange rates
Site/facilities
Competition
Weather
Political
Pressure groups
Force majeure
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 184: Risk Breakdown Structure (RBS)
Risk identification workshops to identify risks under each of the RBS areas
Major areas can be used to structure risk identification interviews
Checklist developed based on the RBS lower levels
Future projects can determine whether each generic risk applies, answering “Yes,” “No,”“Don’t know,” or “Not applicable.”
Upper levels can be used as a PROMPT LIST or result from working with a prompt list

## Slide 185: Brainstorming vs Nominal Group vs Delphi
Brainstorming
  ideas generated by one individual tend to trigger suggestions from other group members
  can be very corrosive
Nominal Group Technique
  generation of ideas by each individual, anonymously recorded, not discussed
  overcomes the shortcomings of brainstorming
  more productive than brainstorming
Delphi technique
  Same creative and convergent response
  Remote method preserving the anonymity of participants

## Slide 186: Questionnaires & Interviews
Questionnaires can provide prompt lists for participants and be useful of engaging more remote stakeholders
Individual interviews can be effective way of engaging senior and important stakeholders, protecting their time and their influence on a group session

## Slide 187: Assumption & Constraints analysis
Assumption is a statement taken for granted as a fact
Constraints things that are considered fixed and either must happen or must not happen
Both should be listed and analyzed (their validity tested). Some can be considered safe.
Threats can be raised for false assumptions and Opportunities for constraints that could be relaxed or removed
Notes: Assumption from assume remember do not make an ASS of U and ME

## Slide 188: Risk Cause, Event, and Effect
Risk Cause
  Describes the source of the risk - the event or situation that gives rise to the risk - often referred to as risk drivers
  Not risks in themselves, but the potential trigger points for risk
  May be either internal or external to the organisational activity under consideration
Risk Event - describes the area of uncertainty in terms of the threat or the opportunity
Risk Effect - describes the impact that the risk would have on the organisational activity should the risk materialise
Notes: Risk Cause, Event, and Effect
Objective: Hosting a BBQ people will still remember for years to come.
Weather forecast: It will be cloudy and rain is expected.
Risk Cause: Bad weather
Risk Event: it might rain during the BBQ
Risk Effect: People will not enjoy the BBQ in the rain

## Slide 189: Assess - Estimate
Ref. 4.6
Estimate
Risk Register
Early Warning Indicators
Probability assessment
Impact assessment
Proximity assessment
Expected Value assessment
Risk Register
(including assessments)
Techniques
Outputs
Inputs
Goals – To assess the threats and the
opportunities to the organisation in terms
of their probability and impact.
Including an understanding of:
The probability of the threats and opportunities
The impact of each threat and opportunity
The proximity of these risks and opportunities
Identify
Assess
Plan
Implement
Communicate
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Notes: Estimate Step - Goals

## Slide 190: Techniques for the Assess Estimate
Probability assessment
  Estimated chance of occurring when NO ACTION is taken
Impact assessment
  Estimated effect of occurring when NO action is taken
Proximity assessment
  When a risk might occur  urgency (helps to select appropriate Risk Response)
Expected value assessment
App. B

## Slide 191: Expected Value assessment
Quantifies risk by combining the cost of the risk impact with the probability of the risk occurring
The simplest form of calculation to employ is:
EV = CoI * P%
where EV = the Expected Value
CoI = the estimated Cost of the risk Impact,
P% = the Probability of the impact occurring
App. B

## Slide 192: Expected Value assessment
If possible quantify risks in terms of money (financial risks)
Other kinds of risk can sometimes be converted to a monetary equivalent for example:
  A 2 week delay may incur additional labour costs of £15.000
  Be aware that this can lead to very controversial situations
App. B
Notes: For instance: Placing a monetary value on life for insurance purposes can be highly controversial
See also appendix B for table B3 for an example how this might aid decisions.

## Slide 193: Assess - Evaluate
Ref. 4.7
Evaluate
Risk Register
Summary risk profiles
Summary expected value assessment
Probabilistic risk models
Probability trees
Sensitivity analysis
Summary risk profile
Relationships and interdependencies
Techniques
Outputs
Inputs
Goal – To assess To understand the net effect
of the identified threats and opportunities on
an activity when aggregated together.
Including, for example, preparation of the following:
An estimated monetary value (EMV) calculation
A risk model
Identify
Assess
Plan
Implement
Communicate
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 194: Techniques for Assess - Evaluate
Summary risk profiles
  Visualization of the total risk
Summary expected value assessments
  Provide the likely financial exposure
Probabilistic risk models:
  Monte Carlo simulation
Probability trees
Sensitivity analysis
Tabel B.6

## Slide 195: The Summary Risk Profile
Colour | Status
None | The risk management action cannot begin until a future specified date: therefore it is not possible to measure progress.
Red | No progress has been made.
Amber | Moderate progress being made on risk management action with little / no evidence of the deliverable.
Green | Progress is being made, commensurate with the stage of the Project, with appropriate evidence of the deliverable.
Blue | Risk management action has been successfully completed and any associated deliverable has been provided.
RAGB
Fig. B.7
Risk
tolerance
line
VH
H
M
L
VL
VL L M H VH
Acceptable risks
Unacceptable risks
Impact (effect)
Likelihood (probability)
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 196: Models
Representation of a real business situation where outcomes are explained by a range of inputs and assumptions
Can be used to represent a wide variety of situations
Can be used to estimate an activity’s total exposure to risk
App. B

## Slide 197: Monte Carlo simulation
Fig. B.8
P10
P50
P90
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Range of outcomes, and the probability of achieving an objective

## Slide 198: Simulations
Objective - to obtain a probability distribution of the likely outcome of an activity, when considering the input variables in combination
Helpful in analyzing cost or time models, where the values of the input data, the variables, (threats, opportunities, costs or durations) may be uncertain
Software commercially available
The thinking behind simulation is similar to the idea of carrying out multiple manual ‘what if’ scenarios
Can be used to estimate an activity’s total exposure to risk
App. B
Notes: Ask candidates if they have experience with for instance the Monte Carlo simulation, else give your own example or refer to the example in the Guidance App B.

## Slide 199: Probability Tree Extract
App. B.9
Project B
Benefits impacted
Project B
end-date impacted
Resources not
released on time to B
Resources released
on time to B
Project B
put on hold
Project B
re-planned
Resources not
released on time
Resources released
on time to B
Project B
increased to cover resources
Project B
Budget overspend
Project B is
descoped
Project B buys
in additional
resource
Project B
is delayed
Project B
budget cut
Project B
Budget protected
Project A
put on hold
Project A
is descoped
Resources released
on time to B
Extra Funding
for Project A
No extra funding
for Project A
Time
overrun
Cost overrun
Project A
overruns
Resources not
released on time to B
Resources released
on time to B
Resources not
released to B
.5
.3
.4
.3
.4
.6
.5
.3
.1
.1
.5
.4
.6
.3
.7
.3
.7
.8
.2
.6
.4
.5
.5
.1
.9
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 200: Sensitivity analysis
App. B
Labour Price Index | 100 |  | 
Material Price Index | 100 |  | 
 | Materials | Labour | TOTALS
Hardware Purchase | 100000 | 3000 | 103000
Installation | 2000 | 10000 | 12000
Systems Analysis & Design | 200 | 15000 | 15200
Programming | 200 | 35000 | 35200
Testing and Implementation | 600 | 5000 | 5600
Documentation | 3000 | 6000 | 9000
TOTALS | 106000 | 74000 | 180000
varying one input in a model can alter the model outcome
© AXELOS Limited 2007. Reproduced under license from AXELOS. All rights reserved.
Notes: This example is taken from another book and is only added as a visual example.

## Slide 201: Plan
Ref. 4.8
Plan
Summary risk profile
Relationships and interdependencies
Risk Register
Existing Insurance
Policies
Lessons Learned
Risk response planning
Cost-benefit analysis
Decision trees
Risk Owner
Risk Actionee
Risk Register (including
Risk Responses and secondary risks)
Risk Response Plan
Techniques
Outputs
Inputs
Goal – To prepare specific management
responses to the threats and opportunities
Identified - ideally to remove or reduce the
threats and to maximise the opportunities.
Ensures as far as possible that the business
and its staff are not taken by surprise if a
risk materialises
Identify
Assess
Plan
Implement
Communicate
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Notes: Plan Step

## Slide 202: Techniques for the Plan Step
Risk Response planning
Cost-benefit analysis
Decision tree

## Slide 203: Risk Responses Planning
Table B.9
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Threat responses
Opportunity responses
Exploit
Avoid
Reduce
(probability and/or impact)
Transfer
(reduces impact only, and often only the financial impact)
Enhance
Share
Accept
Transfer
(not common)
Prepare contingent plans
Notes: Ask delegates to come up with examples of every response type.
Address the difficulty of Avoiding – Example change the approach of a project
Note that Contingency plans seem to be reactive but need to be developed and tested in advance. Ask for common examples of Contingent plans
Explain the difference between Enhance and Exploit – Multiple benefits for Exploit – it could be complete new project or even business line.

## Slide 204: Cost-benefit Analysis
Takes into account all the costs and benefits (such as social benefits and costs)
Gives guidance in economic decision-making
Governments use it to evaluate important investment projects
Places emphasis on externalities
App. B.6.2

## Slide 205: Cost Benefit Analysis
Can be a very imprecise procedure
Difficult to place values on certain important costs and benefits
Results are critically dependent on the discount rate allowed for future costs applied to the calculations
Cost-benefit analysis can be used to determine which risk response actions are the most beneficial
App. B.6.2

## Slide 206: Decision tree
Fig. B.10
No EMV = £680K
Yes EMV = £712.5-£250 EMV = £462.5K
Build prototype?
EMV = £680K
EMV = £712.5K
No
Yes at cost of £250K
Successful launch
0.2
Successful launch
0.75
Rework
0.25
Rework
0.8
20% X £1000K = £200K
80% X (£750K-£150K) = £480K
75% X £800K = £600K
25% X (£600K-£150K) = £112.5K
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 207: Implement
Ref. 4.9
Implement
Risk Owner
Risk Actionee
Risk Register
Risk Response Plan
Update summary risk profiles
Risk exposure trends
Update probabilistic risk models
Risk Progress Reports
Techniques
Outputs
Inputs
Goal – To ensure that the planned risk
management actions are implemented
and monitored as to their effectiveness,
and corrective action is taken where
responses do not match expectations.
Identify
Assess
Plan
Implement
Communicate
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Notes: Implement

## Slide 208: Techniques for Implement
Updated summary risk profiles
  An updated visualization of the total risk
  Alternative visualization can be a scatter diagram
Risk exposure trends
  Using expected value calculation to calculate the combined effect of all residual risks
  It is best practice to separate the threats and opportunities
Updated probabilistic risk models
  To monitor the effectiveness of risk management and to identify further priority areas for action
Notes: Discuss experiences with this technique and benefits and limitations using Appendix B

## Slide 209: Scatter Diagram
Fig. B.11
100
90
80
70
60
50
40
30
20
10
0
0 10 20 30 40 50 60 70 80 90 100
Impact
Probability
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 210: The M_o_R Framework
Identify
Assess
Plan
Implement
Communicate
M_o_R Approach
Risk Register
M_o_R Approach
Risk Management
Policy
M_o_R Approach
Risk Management
Process Guide
M_o_R Approach
Issue Log
M_o_R Approach
Risk Management
Strategy
Management of Risk Principles
Embed and Review
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 211: Embedding and Reviewing M_o_R
Objectives
To show the importance of integrating risk management into the culture of the organisation
To explain how this can be achieved
To highlight the need for regular reviews to ensure risk management is being appropriately and successfully handled across the organisation
What would the organisation be like if the principles were a natural part of the way that work was done across the organisation?
Ref. 5.1
Notes: Embedding and Reviewing M_o_R – Objectives

## Slide 212: Changing the culture for Risk Management
Ref. 5.3
Corporate Governance creates sense of urgency
Vision
Where we want to be
Defined structure and composition
of the changed organisation (Blueprint)
Benefits
Identified &
profiled in
the Business
Case
Projects
Delivered
Process changes
incorporated into the Business
Outcome
Achieved
M_o_R Embedded
M_o_R Ongoing Embed Review
Ongoing Benefits Management
A Programme (using MSP®)
Embedding a risk culture
Long-term goal with a clear, achievable plan
Changing the ‘mindset’
Can take up to a couple of years to fully establish
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Notes: Integrating M_o_R

## Slide 213: Measuring the value
Questionnaires
  Ad- hoc distribution of paper based or electronic questionnaires to gauge how much has been absorbed
Benchmarks
  After establishing a baseline which to measure against then measuring the impact a risk management awareness programme has in an organisation, or level of impact of introducing fresh or new risk management practices
Cost Benefit
  Should be measured against cost (time or money) to provide an accurate measure of the value
Education
  Measuring benefits from an education, training or awareness programme through sampling understanding and knowledge within the staff via questionnaires
Ref. 5.4

## Slide 214: Measuring the value
Supported by senior management
Policies and benefits understood by all
Transparent and repeatable risk management framework
Supported by a culture of well thought-through risk taking and innovation
Linking of M_o_R with objectives
Assessment and management of the risks when working with partners
Monitoring and regular review of risks based on ‘no-blame’
Sharing of lessons learned
Reporting and escalation of risks within appropriate timescales
Ref. 5.4

## Slide 215: Overcoming the common Barriers to success
Policies, processes and strategies will not automatically lead to robust, effective and efficient risk management practices
A series of barriers or obstacles will always be in the way
Understand the barriers, deal with them appropriately
Ref. 5.5 and 4.2
Notes: See also the relationship with the common process barriers – page 37 (4.2)
Changed slide to delete overlap with added slide supporting factors

## Slide 216: Overcoming the common Barriers to success
Supporting factors
Senior management commitment to adequately support middle and lower management
Training, knowledge of risk management and formal risk tools and techniques
An adequate Risk Budget to support that risk management is important
To reward productive risk management behavior and investment is most effective
Ref. 5.5 and 4.2
Notes: Also point to the list in the Guidance

## Slide 217: Modifying Behaviour towards M_o_R
Behaviour should support risk management:
Integrate into job descriptions
Personal success and benefit/recognition
Integrating risk management into processes
  Business
  Programme
  Project
  Operational
Ref. 5.5

## Slide 218: Sr. Management Commitment & Support
M_o_R implementation can be delegated
Accountability for understanding and managing risk remains with nominated person at board level
Sponsorship, responsibility and endorsement must be clearly demonstrated
Senior and middle management are therefore given responsibility for:
  The creation of a Risk Framework
  The creation of a management infrastructure
  The setting of performance objectives aligned to the framework and the inclusion of risk in the appraisals process
Ref. 5.4
Notes: Ask the delegates how this commitment might be achieved.
Refer to page 59/60 for the list of useful methods.

## Slide 219: How to Build & Develop Awareness
Use Risk management champions
Including risk responsibilities and activities in job descriptions, objectives and staff appraisals
training new staff
Information on the intranet
Publishing Articles, Newsletters etc.
Promotion - using simple products
Ref. 5.5
Notes: Building & Developing Awareness

## Slide 220: Identifying & establishing opportunities for change
Changes in organisational structure and/or personnel
Other change management activities
Introducing new or changed standards
Unexpected occurrences or failures within an organisation
Ref. 5.6

## Slide 221: M_o_R® Practitioner - Day 3

## Slide 222: Embedding and Reviewing
The Health Check
Maturity Models

## Slide 223: M_o_R Health Check
Check the ‘health’ of risk management where can we improve
Used for self-assessment, peer review or external assessment
Most useful when preparing and carrying out an enterprise-wide assessment
Also used for assessments of specific programmes, projects or operational activities
The health check might prove useful:
  before or as complement to an gateway review
  when developing an annual operational plan
App. C

## Slide 224: M_o_R Health Check Process
The health check should be formally administered and repeated to monitor changes over time
Each administration of the health check will occur using these steps
App. C
Data Analysis
Identify trends and patterns
Note deficiencies
Note strengths
Identify three to five key themes
Conduct intermediate review with the sponsor
Identify recommendations.
Preparation
Define ToR based on the sponsor’s needs
Define roles and responsibilities
Select a review team
Collect background information for the team
Brief the team and share information
Refine the Health check approach
Refine the question set
Define the necessary interviews
Schedule interviews (as appropriate).
Data Collection
Review written documentation (as appropriate) note individual findings
Conduct interviews (as appropriate) and document findings from each.
Review and Report
Draft report
Conduct final review with the sponsor
Finalise report.
Notes: See page 111

## Slide 225: Health Check Questions
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.
Each Principle followed by a set of questions
Affirmative response identifies an aspect of the principle that has been applied
Negative response identifies a lack of comprehensive application of the principles
The more questions that are answered in the affirmative, the closer the application of risk management approaches good practice
App. C

## Slide 226: Maturity model
App. D
Competencies
attained or
desired
capabilities
Maturity
Model
constructed
as a matrix
Levels
sequence for
developing
Capabilities
Criteria
primary risk
management
practice
Levels - “stepping stones” for Incremental Improvement
Assessment Criteria used to describe the quality of the processes within each level
Competencies - how well developed the M_o_R practices should be for each of the different levels
© AXELOS Limited 2010. Reproduced under license from AXELOS. All rights reserved.

## Slide 227: NOT EXAM MATERIAL

## Slide 228: Risk Specialisms
Business continuity management
Incident (crisis) management
Health and safety management
Security risk management
Financial risk management
Environmental risk management
Reputational risk management
Contract risk management
Notes: Risk Specialisms

## Slide 229: Business Continuity Management (BCM)
Identifies potential threats and the impact these may have to Business Operations (BAU)
Provides a framework to building organizational resilience for an effective response
Safeguards the interests of key stakeholders, reputation, brand and value creating activities
BCM includes disaster recovery, business recovery, crisis management, emergency management, product-recall and contingency planning
App. E.1
Notes: Business Continuity Management in a Risk Context
BCM complements wider risk management programme
Risk management is integral part of BCM
BCM incorporates risk identification, assessment and control in relation to the activities, products and services on which the organisation depends
Organisations must take a risk informed view on the responses that may be needed when disruption occurs
Organisations must be confident that it will manage its risks through any consequences without unacceptable delay in delivering its products or services

## Slide 230: Risk Specialisms
Business continuity management
Incident (crisis) management
Health and safety management
Security risk management
Financial risk management
Environmental risk management
Reputational risk management
Contract risk management
Notes: Risk Specialisms

## Slide 231: Incident and crisis management
Incident is an event that can lead to loss of or disruption of an organization BAU
  + if not managed can escalate into an emergency, crisis or disaster
Crisis is an occurrence and/or perception that threatens the operation (BAU), staff, shareholders value, stakeholders, brand, reputation, trust and/or strategic business goals
Crisis Management is about the wider impact of a BCM emergency, event, incident or crisis until it is under control/contained without impact or the BCM plan is evoked
App. E.2
Notes: Disaster Recovery Planning
A series of processes that focus on recovery processes, principally in response to disasters
This activity forms part of business continuity planning, not the totality
Primary aim of the incident management plan:
Safety of all affected individuals
Contain the disaster to minimise loss
It must have board level support
Budget for development, maintenance and training

## Slide 232: Risk Specialisms
Business continuity management
Incident (crisis) management
Health and safety management
Security risk management
Financial risk management
Environmental risk management
Reputational risk management
Contract risk management
Notes: Risk Specialisms

## Slide 233: Health & safety management
Preventing people from being harmed by work or becoming ill,
  By taking precautions and
  Providing a satisfactory working environment
There are rules which require everyone NOT to put themselves and others in danger
The law also protects the public from workplace danger
App. E.3
Notes: Health and Safety
Organisations must protect its most valuable asset – ‘people’
  major responsibility
  legal obligation
H & S legislation relates to all aspects of people within a working environment
Specialist area requiring adequate training as well as fully assigned responsibility for ensuring adequate controls are in place

## Slide 234: Risk Specialisms
Business continuity management
Incident (crisis) management
Health and safety management
Security risk management
Financial risk management
Environmental risk management
Reputational risk management
Contract risk management
Notes: Risk Specialisms

## Slide 235: Security risk management
Protection against any loss of or danger that would have a
detrimental (negative) effect on an organization’s
Physical assets
Personnel and
Information assets.
All of these assets are essential for the day-to-day operations (BAU)
App. E.4
Notes: Main areas for consideration
  information
  personnel
  physical
  Technical NOT technical anymore
Security - about maintaining the
  Confidentiality (of an asset)
  Availability (of an asset)
  Integrity (of an asset)
Security risk management looks at, assesses and develops an appropriate approach or treatment for risks relating to the security of those assets.
Threats - activities that could affect the confidentiality, availability or integrity of the asset
Same risk management principles, techniques and process should be applied to security risks as are applied to any other risks

## Slide 236: Risk Specialisms
Business continuity management
Incident (crisis) management
Health and safety management
Security risk management
Financial risk management
Environmental risk management
Reputational risk management
Contract risk management
Notes: Risk Specialisms

## Slide 237: Financial risk management
The practice by which an organization optimizes the manner in which it takes financial risk this includes:
  Monitoring of financial risk taking activities
  Upholding relevant financial and operational policies and procedures through appropriate controls
  Production and distribution of financial risk related reports
Four aspects of financial risk management on which success depends:
Positive corporate culture
Actively observed policies and procedures
Effective use of technology
Independence of risk management professionals
App. E.5
Notes: Financial risk management
Four aspects of financial risk management on which success depends are
closely related to principles of overall good risk management practice, and have been specifically publicized following a number of financial risk management failures

## Slide 238: Independence
Risk Managers have reporting lines - independent from those of risk taking functions
Risk Takers have no input on the performance reviews, compensation or promotion of risk managers, and vice versa
Employees cannot fulfil both roles
  those hired into financial risk management undertake the role of financial risk management:
  those hired as risk takers undertake the role of risk takers
Risk Managers do not take risks on the firm’s behalf, they help identify risks quantify and qualify those risks
Notes: Independence

## Slide 239: Risk Specialisms
Business continuity management
Incident (crisis) management
Health and safety management
Security risk management
Financial risk management
Environmental risk management
Reputational risk management
Contract risk management
Notes: Risk Specialisms

## Slide 240: Environmental risk management
Risks in this area are:
Pollution, land erosion, deforestation, fire damage to natural resources, etc
An organisation should:
Identifies and controls the impact of its activities, products or services
Improves its environmental performance continually
Implement a systematic approach to setting environmental objectives and targets, achieves these and demonstrates that they have been achieved
App. E.6

## Slide 241: Risk Specialisms
Business continuity management
Incident (crisis) management
Health and safety management
Security risk management
Financial risk management
Environmental risk management
Reputational risk management
Contract risk management
Notes: Risk Specialisms

## Slide 242: Reputational risk management
Reputation is one of the most important assets of an organisation
Most common threats to reputation are:
  Failure to comply to regulations
  Failure to deliver minimum standards of service
Reputation is concerned with how an organisation is perceived by its stakeholders. Good communication is an essential element of building and protecting reputation.
App. E.7

## Slide 243: Risk Specialisms
Business continuity management
Incident (crisis) management
Health and safety management
Security risk management
Financial risk management
Environmental risk management
Reputational risk management
Contract risk management
Notes: Risk Specialisms

## Slide 244: Contract risk management
The fase where a supplier delivers the good according to the procuring authority’s specification.
Failure can be expensive in human, financial and reputational terms
It is therefore key to successful delivery and value for money
App. E.8